Missouri GIS Advisory Committee

2004-2005 Work Plan Status Report

#### Vision

Improving Missouri with Geographic Information Systems

#### Mission

Foster cooperation among state, local, and federal agencies, educational institutions, private industry, and others in the field of Geographic Information Systems (GIS); provide guidance for the Missouri Spatial Data Information Service (MSDIS) in fulfilling the objectives of the Missouri GIS Strategic Management Plan (SMP); develop GIS standards for the state; provide an arena for discussions of relevant GIS issues; provide expert advice to the chief information officer (CIO) and the GIS community on GIS related issues; facilitate resolution of GIS issues impacting the state; coordinate and facilitate statewide training as needed; and work together with other states on standards and other GIS issues.

## Theme Area 1: Outreach/Education/Training

TARGET OUTCOME: Increase visibility and understanding of the work of the MGISAC so the committee’s purpose, mission, and work is understood more fully by state and local government agencies, the Missouri General Assembly, private enterprise, and others.

OBJECTIVE: Expand visibility and understanding of MGISAC’s work within Missouri.

STRATEGY: Increase the utility of the Web site for MGISAC by posting information such as meeting dates, meeting agendas, meeting minutes, and the like, in a timely manner.

MEASURE:  The Communications subcommittee will track contributions to and activity on MGISAC Web pages.

ACTION: Post regular updates of committee and subcommittee meeting announcements, agendas and minutes to the website (Communications subcommittee, MGISAC webmaster).

STATUS: Full committee meeting minutes are available on the web site as are subcommittee meeting minutes for those subcommittees which have met and taken minutes. The MGISAC web site home page has been kept current with upcoming meeting announcements and other relevant news. The MGISAC web site is indexed by the State search engine; any visitor to the State search page seeking information on GIS topics will likely receive results from the MGISAC web site.

ACTION: Finish MGISAC website transition to new look and begin expanding it for greater outreach opportunities.

STATUS: New web pages have taken on new format and new subcommittee areas have been created containing minutes and other relevant information as submitted. The new format is a response to a directive from the State ITSD to standardize State-affiliated websites.

STRATEGY: Use written communication through the Office of Information Technology to provide annual updates to ITAB.  Develop articles and participate in different media venues.

MEASURE:  Completion and submission of updates to OIT. Track number, size, and type of conferences attended. Monitor posting of white papers, standards, I-Team plans, and the like, on MGISAC Web site and in appropriate media outlets.

ACTION: Represent MGISAC at monthly ITAB meetings (MGISAC ITAB Liaison).

STATUS: Either Jeff Falter or Tony Spicci have attended every meeting and provided an update.

ACTION: Participate in ITAB strategic planning session (MGISAC Chair, other MGISAC members).

STATUS: No strategic planning sessions this year.

ACTION: Provide Annual Report to ITAB in June and provide updates (as necessary) at ITAB monthly meeting (MGISAC Chair, MGISAC ITAB Liaison).

STATUS: Provided monthly updates; Annual Work Plan report submitted in September 2005.

ACTION: Post annual State’s Activities and State Summary to National States Geographic Information Council (NSGIC) website (MGISAC Chair, Communications Subcommittee).

STATUS: Completed September 2004

ACTION: Update State GIT profile (Communications subcommittee)

STATUS: No action.

ACTION: Publish MGISAC outcomes of work plan tasks to website and distribute those elements to appropriate constituencies via list serve e-mail (Various committees).

STATUS: Annual Work Plan report posted September 2005

OBJECTIVE: Host and attend conferences in state and region.

STRATEGY: Organize and host the state GIS conference with associated educational workshops in odd years to promote MGISAC activities and the development of professional networks and user groups. Actively participate in and support the Mid America GIS symposium with associated educational workshops in even years to allow for regional interaction of GIS professionals and the sharing of knowledge, processes, and protocols. Identify conferences and events for MGISAC and/or MSDIS to participate in.  Utilize the MGISAC exhibit booth to increase presence at conferences and events.

MEASURE: Odd years – State conference held and attendance and participation reported. Even years – Mid America GIS Consortium (MAGIC) symposium held and attendance and participation of Missourians reported. Log conferences attended by membership as representatives of the MGISAC.

ACTION: Plan for the 2006 Mid America GIS Consortium (MAGIC) symposium with MAGIC Consortium. (Education and Outreach Subcommittee).

STATUS: MGISAC members and MSDIS staff are significantly involved in the planning of the 2006 Symposium – chairing or co-chairing subcommittees; recruiting plenary speakers, developing the program, etc. The 2006 Symposium is to be held April 23-27, 2006 in Kansas City, MO.

ACTION: Host a display booth in the 2005 MOGIS conference exhibit hall and provide appropriate materials to conference attendees (Education and Outreach Subcommittee).

STATUS: Completed.

ACTION: Host a display booth, participate in and/or sponsor the following state conferences / meeting:  Missouri Mappers’ Association (MMA), Missouri Society of Professional Surveyors (MSPS), Missouri Assessors Association (MAA), or others as appropriate (Education and Outreach Subcommittee).

STATUS: MSDIS staff hosted booths for both MSDIS and MGISAC at the Missouri Digital Government Summit; a booth at Missouri Mappers’ Association (MMA), a lecture at Missouri Assessors Association (MAA), and a booth at Missouri Society of Professional Surveyors (MSPS).

ACTION: Participate / send member attendees to the following national conferences/meetings:  NSGIC, FGDC, NASCIO and numerous others listed in Appendix A (Education and Outreach Subcommittee).

STATUS: MSDIS sent two representatives to the NSGIC 2004 Annual meeting in Austin.  One staff member participated in the CAP Kickoff meeting in Denver, CO.  Staff members regularly attend regional meetings such the Mid-America Geographic Information Consortium (MAGIC) and the Land Based Classification Standards Meeting in Topeka, Kansas.  Three staff members attended the USGS NGPO listening Session at Tan-Tar-A.

ACTION: Plan and host the 2005 Missouri Conference (E&O Subcommittee).

STATUS: Completed with 312 participants. MGISAC members and MSDIS staff were significantly involved in the planning of the 2005 conference – chairing or co-chairing subcommittees; recruiting plenary speakers, developing the program, providing web registrations; page setup and facilitating setup of computer systems (with MODoT’s generous assistance) for conference workshops.

ACTION: Record the participation of MGISAC members at conferences/meetings.

STATUS: Refer to appendix A

OBJECTIVE: Expand GIS Day participation

STRATEGY: Participate in, encourage, and support annual GIS day events.

MEASURE; Create a separate MGISAC Web page that contains available resources (presentations, vendor provided, organizations, events calendar) along with a feedback interface that GIS Day participants and sponsors can use to share their events/stories.

MEASURE; Post to the MGISAC web site a summary of activities and create a white paper that can be provided to MGISAC members and their affiliated organizations for use in articles/press releases.

MEASURE; GIS Day activities will occur or be sponsored in each of the represented entities of the MGISAC and be included in the annual report.

ACTION: Create a links for GIS Day activities and web pages, including those hosted by MGISAC (Education and Outreach Subcommittee).

STATUS: None provided to include.

ACTION: Reference (on the MGISAC web page) MGISAC GIS Day activities (E&O, Communication Subcommittees)

STATUS: None provided to include.

ACTION: Plan annual GIS Day and report on activities (in Committee minutes) at the December meeting (E&O Subcommittee).

STATUS: MSDIS staff participated in and hosted a booth for MGISAC/MAGIC at the GIS Day celebrations hosted by ESRI at the St. Louis Zoo.

OBJECTIVE: Educate and inform citizenry about GIS issues. 
STRATEGY: Develop introductory GIS materials for exhibit booth as well as informational materials for managers, legislators, the public, and so on.

MEASURE:  Ensure that printed copies are available for participant use at conferences                                  and that information is available via the MGISAC Web site.

ACTION: Organize a GIS awareness event at the Capitol for legislators and staff (E&O Subcommittee).

STATUS: Incomplete

ACTION: Review and update (on an annual basis) the MGISAC brochure (Education and Outreach Subcommittee)

STATUS: Incomplete

STRATEGY: Participate in national organizations and initiatives and inform citizenry about these issues and opportunities.

MEASURE: Utilize the MGISAC Web site and monthly MGISAC meetings to provide information through regular updates and reports.

ACTION: Maintain an active membership in NSGIC and designate a member to represent Missouri.

STATUS: Tony Spicci serves as Official State Representative and in-coming President of NSGIC. Tim Haithcoat is another member of MGISAC who Chairs both the NASA Liaison Committee and the Geospatial Enterprise Architecture Committee.

ACTION: Capture participation in minutes and post to website (Secretary, Communications subcommittee).

STATUS: None provided to include.

OBJECTIVE: Facilitate metadata development.

STRATEGY: Increase utility of data holdings by working with data producers to aid in the development of Federal Geographic Data Committee (FGDC)-compliant metadata for their data contributions to the MSDIS Web site.

MEASURE:  Nearly all data submitted to MSDIS will have FGDC compliant metadata with data submissions. Exceptions will be limited and considered on a case by case basis (e.g., Census Bureau data).

ACTION: Post statement defining metadata requirements on MSDIS website.

STATUS: Changes are being made by MSDIS, as this document is being annotated. This objective, however, will be met as part of a larger effort to appeal to potential suppliers of data for the clearinghouse.

ACTION: Screen all in-coming datasets for FGDC-compliant metadata.

STATUS: MSDIS performs this function as data is submitted.

OBJECTIVE: Expand knowledge and awareness of Geographic Information Technology (GIT) and training opportunities at the local government level.

STRATEGY: Develop and foster a liaison group of local government participants to coordinate state GIT activities with local activities.

STRATEGY: Identify and post inventory of training opportunities on Web site and update quarterly.

MEASURE: Verify that information is available and that quarterly updates are made.

ACTION: Identify and post inventory of training opportunities on the web site and update quarterly (E&O Subcommittee).

STATUS: MSDIS posts this information and distributes through list serve email.

ACTION: Promote GIS training events. (E&O Subcommittee).

STATUS: MSDIS staff promote all known training opportunities via the list servers and through regular education and outreach efforts.  The list serve administrator is also a MSDIS staff member.

OBJECTIVE: Identify problems and create solutions for Geospatial Information Technology (GIT) startup, development and maintenance at the local government level.

STRATEGY:  Establish a caucus of Missouri local government GIT users that will function as the MGISAC local government subcommittee

MEASURE:  Develop a name and logo write a mission statement, and enlist local government GIT users to populate the caucus

ACTION: Rollout the new caucus name/logo and mission (create a one-page mission document) and solicit local government membership at the February 2005 MGISAC conference. Later, hold first "LOGIC" membership meeting. (Spring 2005)

STATUS: The Local Government Subcommittee has been activated and is holding regular meetings following the monthly MGISAC meetings.  MSDIS participates (3 staff members) in “LOGIC” performing varied functions.

ACTION: Post information for caucus creation, development and activities on MGISAC website, subcommittee page, including: meeting times, points of contact and Listserv.

STATUS: Not complete.

ACTION: Evaluate and use results of MSDIS and East-West Gateway Council of Governments (EWGCOG) GIS surveys, along with membership expertise, to formulate specific outreach efforts to the local governments. (Spring/Summer 2005). Implement other outreach efforts -- to be determined. (E.g., Identify and conduct pilot projects with selected local governments; create whitepapers, Powerpoint presentations or other informational pieces for local governments.)

STATUS: The Local Government Subcommittee is evaluating these surveys and developing a plan of action for their subcommittee.  MSDIS FGDC/USGS Cooperative Agreement Program funding has led to regional trainings of local government staff, new data submissions for the National Map and a stronger partnership with Local Government.

ACTION: Implement other outreach efforts – to be determined. (e.g., Identify and conduct pilot projects with selected local governments; create whitepapers, Powerpoint presentations or other informational pieces for local governments.)

STATUS: Pilot projects have been completed for 2-3 counties. Information about MGISAC activities were presented at the Missouri Mapper’s Association (MMA) conference in 2004.

Theme Area 2: Data Development

Target Outcome: To promote accessibility of all GIS data within Missouri.

OBJECTIVE: Establish and publish an inventory of data holdings available at the MSDIS.

STRATEGY: Inventory the data holdings available at the MSDIS, grouping them thematically and posting this information in a searchable format.

MEASURE: Completion and maintenance of this inventory activity on MSDIS Web pages.

ACTION: Review MSDIS activities and progress in this area.

STATUS: Initial phase of this objective completed. Metadata for the data warehoused at the MSDIS are searchable. A data theme list is also available, but a comprehensive inventory is in progress.  A national standard for keywords was implemented to allow the MSDIS holdings to be in synch with other federal data warehouses.  This required a complete review / edit of all metadata records and their re-posting on MSDIS.

OBJECTIVE: Identify gaps in the data inventory.

STRATEGY: Identify incomplete or unavailable data that are needed by the widest audiences.

MEASURE: Use a variety of conduits for assessing data needs and establish priorities for data development efforts.

ACTION: Utilize the recommendations of the MGISAC Homeland Security subcommittee regarding data needs and prioritization of data development efforts.

STATUS: In June of 2005, the MGISAC Homeland Security subcommittee provided a list of eighty data layers deemed to be of the highest priority. This list is meant to act as a guide for agencies to focus their efforts.

ACTION: Conduct two meetings per year where invitees are asked to report on data development activities, grant utilization, and data needs.  One of these meetings will be held in conjunction with the Missouri GIS conference or the Mid-America GIS Consortium (MAGIC) conference.

STATUS: One public meeting was held in Rolla on July 8, 2004 in conjunction with a regularly scheduled MGISAC meeting.  A second public meeting was held in Osage Beach on February 22, 2005 in conjunction with the biennial Missouri GIS conference.

ACTION: Research survey tools to collect information about data needs via the World Wide Web.

STATUS: The subcommittee members are anticipating the release of a federal web application that will facilitate the gathering of data needs.

Target Outcome: To facilitate the development of needed GIS information in Missouri.

OBJECTIVE: Develop an implementation plan for each Missouri framework data layer identified by the MGISAC.

STRATEGY: Identify data stewards and develop data specific implementation plans for data layers. Publish plans on Web site for review, comment, and revision.  Publish final draft of implementation plans on MGISAC Web site.

MEASURE: Completion of data development plans for identified thematic layers and facilitate other data development efforts.

ACTION: Use the Missouri Adaptive Enterprise Architecture (MAEA) Digital Ortho-imagery Product Component to develop plans for acquiring leaf-off imagery at a variety of resolutions that satisfy the majority of needs in the state.

STATUS: The subcommittee membership has grown in response to collaborative efforts to acquire imagery, and the subcommittee has piloted an ‘imagery needs survey’ that will seek to identify regional and local government imagery needs and partners.   Federal and State government partners have been approached and commitments are being firmed up for this data acquisition effort, which is likely to take place in the spring of 2007 and spring of 2008.

OBJECTIVE: Increase the amount of data development funded by grants and developed through partnerships.

STRATEGY: Identify federal and private grant opportunities that may aid data development activities and make the information available to interested parties.  Collect information on data development activities that utilize grant funds and make the information available to interested parties.

MEASURE: Availability of information regarding grant opportunities and data development activities partially or wholly funded with grant monies.

ACTION: Research sources for grant opportunities related to GIS and data development and make them available via the MGISAC Web site.

STATUS: Some research has been conducted but Web pages have not yet been completed for posting.

ACTION: Request that organizations participating in semi-annual data development meetings report on efforts utilizing grants funds.  Include this information with the summaries from those meetings and make the information available via the MGISAC Web site.

STATUS: This information was requested at the two public subcommittee meetings this past year but very little information was received.

MEASURE: Availability of information regarding data developed through partnerships.

ACTION: Research documents regarding successful data development partnerships and make them available via the MGISAC web site.

STATUS: Incomplete.

Theme Area 3: Missouri Adaptive Enterprise Architecture

Target Outcome: Integrate GIT into the Missouri Adaptive Enterprise Architecture (MAEA) Plan – providing guidance for the development and enhancement of the State Information Technology infrastructure.

OBJECTIVE: Solicit adequate GIT representation and participation to allow development and review of state architecture components as the MAEA Plan progresses.

STRATEGY: Working with the OIT, appoint appropriate GIT representatives for the domain areas and committees generated by the MAEA to make recommendations for implementation of architectural elements relevant to GIT. Identify within these discussions those federal, state, and local initiatives that the MAEA would impact.

MEASURE: Active attendance and participation of the MGISAC designees in the activities of the MAEA domains.

ACTION: Maintain an Architecture Subcommittee to staff the Information Domain / GIT Discipline to assist with the development of the GIT elements of the MAEA (Architecture subcommittee, GIT Discipline Team).

STATUS:  This action is on hold. The GIT Architecture Subcommittee was maintained through December.  Several members became involved with agency activities as well as several members moved on to different posts outside of state government.  A decision was made to create drafts of GIT artifacts with smaller teams and then use the MGISAC as a whole for the review of those documents.

ACTION: Establish an extended Architecture Subcommittee to review Domain / GIT Discipline artifacts to assist with the permeation of GIT across the MAEA (Architecture subcommittee) for the purpose of disseminating the work to a broader GIS community.

STATUS: The MGISAC as a whole is being used for the review of those documents. Specific teams of individuals are created to develop first drafts for posting to the MGISAC.

ACTION: Identify and aid in the assessment of GIT product level information for integration into the MAEA through participation in surveys or other related information gathering efforts (extended MGISAC, as needed by the Architecture Subcommittee).

STATUS: The MGISAC and extended geo-community (through the MSDIS mailing list) have been used as targets for surveys related to GIS and Addressing.  As well, some data gathering for Interactive Internet Mapping Services (IIMS) was solicited.

ACTION: Review of MAEA GIT Discipline Outline and prioritization by MGISAC for these activities.

STATUS: Incomplete

Target Outcome: To promote interoperability and standardization among core data layers being developed by the state and local government agencies and organizations.

OBJECTIVE: Develop and endorse of geospatial standards for database development and attribution.

STRATEGY: Review existing state, federal and international geospatial standards. Create or add new components, modify components, or adopt reviewed standards. Release drafts through MSDIS, MGISAC, and subcommittees for peer review and comment. Revise as appropriate and publish final standards within MAEA.

MEASURE: Review and promotion of four (4) geospatial standards by the MGISAC to the MAEA.  Incorporate these 4 standards with associated compliance components and descriptions within the MAEA Framework.

ACTION: Disseminate geospatial standards for active review process with constituencies coordinated through the MGISAC and the extended Local Government Review group (i.e., Architecture, Local Government Subcommittees).  The possible targeted standards include:

- Address Standard (final draft)

- Road Centerline Standard (initial draft stages)

- Other Transportation Standards

- Spatial Data Accuracy Standard

- Hydrography Standard

- Symbology Standard

- Cadastre Standard

- Elevation Standard

- Geodetic Control Standard

- Governmental Unit Boundaries Standard

- Orthoimagery Standard (update)

- Geospatial Metadata (update)

STATUS: The Orthoimagery Standard has been adopted by the State Architecture as well as the Geospatial Metadata Standard. The Addressing Standard is finally completed and has become part of the state architecture.  The Road Centerline standard has been distributed and comments received.  This standard will be split into three elements: 1) Geographic, 2) Linear Referencing System, and 3) Addressible Centerline.

As well, compliance components for GPS systems (Survey, Mapping, and Recreational grades) and GIS systems were developed.  For GIS systems a product component was developed for four (4) GIS products.  For Geospatial Metadata, product components were developed for six (6) metadata tools.

Theme Area 4: Policy and Legislation

Target Outcome: Coordinate, monitor, and support policy and legislation that impacts geographic information within the state.

OBJECTIVE: Coordinate and support policy and legislation that affects statewide GIT activities.

STRATEGY: Working with the OIT and sister organizations (e.g., Missouri Mappers’ Association, Missouri Assessors, Missouri Surveyors, etc.), research, review, track, and report on policy and legislation before the state legislature.

MEASURE: Provide monthly updates to MGISAC members.

ACTION: Designate a legislative liaison to monitor legislation and opportunities and report back to MGISAC.

STATUS:  A designation was not made.  Tim Haithcoat took on the role of Chair of the Policy Committee to initiate some action.  Senate bill 210 and House bills 349 and 415 were tracked.  Meetings were held in conjunction with the Missouri State GIS Conference to continue discussion and debate.  Following the Missouri Conference a response to these bills was drafted and forwarded by the MGISAC Chair to the Office of the CIO.

OBJECTIVE: Develop a resource base for sharing information about access and sharing policies for use by the broader G.I. community in the state.

STRATEGY: Identify, compile, and review within committee resources related to the approaches and working agreements in the areas of data access and sharing to develop a resource base of approaches that the Missouri GIS community can utilize based on their needs and requirements.

MEASURE:  Policy Subcommittee has established a presence on the MGISAC web site; at least 1-2 examples of data access and sharing policies are available; and a draft of an executive summary outlining Missouri information status is complete.

ACTION: Create a Policy Subcommittee list serve discussion within the MGISAC web site for posting of policy resources (with links), scheduled meetings, and meeting minutes.

STATUS:  A Policy Subcommittee has been created but it has not built a web presence on the MGISAC website.

ACTION: Compilation of data access and sharing approaches for policy resource page.

STATUS: Compiled, but not posted.

ACTION: Generate an executive summary of Missouri’s public versus confidential information status in the form of a white paper (Policy Subcommittee).

STATUS: Completed.

### Theme Area 5: Statewide Coordinator

Target Outcome: Establish a State GIS Coordinator position.

OBJECTIVE: Establish a position to coordinate and facilitate geospatial technology activities for Missouri.

STRATEGY: Define the duties, roles, and responsibilities for the position. These are to include, but are not limited to, facilitating organizational cooperation, championing GIT in state government, coordinating funding, developing legislative action items, and acting as liaison to federal, regional, and local organizations. Create a justification package for the position based on this information. Investigate and establish funding mechanism and define the placement and authority of the position in state government.

MEASURE: Delivery of justification package and funding scenario for the coordinator position to the OIT.

ACTION: Define the duties, roles, and responsibilities and create a justification package for the creation and hiring of a State GIS Coordinator.  (MGISAC Chair, OIT).

STATUS: Delivered to State Chief Information Officer (CIO) in June 2005.

### Theme Area 6: Homeland Security \ Emergency Management

Target Outcome: Integrate GIT into Homeland Security and Emergency Management \ Response activities.

OBJECTIVE: Promote and coordinate use of GIT in federal \ state \ regional \ local emergency management \ response.

STRATEGY: Establish Homeland Security liaisons in various organizations and offices. MGISAC Homeland Security Subcommittee members will participate in federal, state, regional, and local meetings where GIS and its application in public safety can be promoted and coordinated.

MEASURE: Logged, active participation by liaisons in meetings with monthly reports to the MGISAC.

ACTION: Communicate with state Homeland Security and Emergency Management offices on integrating GIS in current or upcoming projects.  Identify other key agencies and identify or assign a liaison for each.

STATUS: Homeland Security and Emergency Management offices have undergone major structural changes this year.  Contact has been made with new management on the status of GIS in Missouri homeland security.

ACTION: Actively seek out GIS information on grant opportunities, grant proposals that garnered awards, and spending.  Work with the data development subcommittee to supplement grants web page with specific links to Homeland Security.

STATUS: Incomplete

OBJECTIVE: Develop and prioritize an inventory of necessary data layers to support Homeland Security Emergency Response.

STRATEGY: Evaluate for Missouri the Homeland Infrastructure Foundation Level Database (HIFLD) and Homeland Security Infrastructure Program (HSIP) documents and the data needs listed as to their status and level of availability.

MEASURE: Completion of data inventory and prioritization of layers.

ACTION: Create an updated data inventory list of layers essential for Homeland Security.

STATUS: A specialized inventory list for Missouri homeland security was created from the Homeland Infrastructure Foundation Level Database (HIFLD).

ACTION: Prioritize essential data layers and coordinate data development efforts with the Data Development Subcommittee.

STATUS: Layers from the spatial data inventory were prioritized, and a list of 80 critical layers was submitted to the Data Development Subcommittee in June of 2005. This list is meant to act as a guide for organizations to focus their efforts.

### Theme Area 7: Management and Oversight

Target Outcome: Coordination and oversight of GIS related activities in Missouri.

OBJECTIVE: Review MSDIS operations and budget and provide recommendations.

STRATEGY: Review quarterly MSDIS’ operational status and financial reports relating to MGISAC activities, and ensure that activities align with the MGISAC Strategic Plan where appropriate.

MEASURE: Quarterly reports generated and presented to the MGISAC for review. MGISAC will review the MSDIS work plan annually.

ACTION: Review and approve quarterly reports as presented (MGISAC).

STATUS: MSDIS has submitted quarterly and annual reports in a timely manner – additionally MSDIS has developed a paperless method of reporting by offering its reports online at both the MSDIS and MGISAC web sites.

OBJECTIVE: Maintain proactive planning and review process for activities of the MGISAC and the MSDIS.

STRATEGY: Ensure that the various MGISAC subcommittees meet regularly so that coordination and development of work plans, tasking, and tracking metrics for outcomes are reviewed and revised as needed.  Specifically, the strategic planning activity needs review and revision biennially.

MEASURE:  Creation and review of annual work plan for MGISAC and MSDIS; biennial review and update of Strategic Plan.

ACTION: Review and approve MSDIS annual work plan (MGISAC).

STATUS: Incomplete